## Pre-Design
DESIGN STAGE DELIVERABLE CHECKLIST
This checklist is intended to serve as a communication tool clarifying expectations of drawing content and submittal requirements at various stages to inform University Stakeholder's review of major design issues for practicality, aesthetics, sustainability, campus planning impacts and cost effectiveness. It is not a complete or exhaustive list of requirements and additional drawing information or submittals may be required based on individual project needs. Refer to the OSU Building Design Standards for complete requirements of the University. Minimum drawing requirements for the establishment of GMPs are to be coordinated between the DB/CMR and A/E based on contract requirements.
Any item not included on the drawings or in the submission require a comment. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
Pre-Design
Deliverable categories | Deliverables |  | Checkbox (X) | Comments
General | Sustainability Charette Narrative | Including Embodied Carbon Study
Sustainability Applicability Matrix (SAM)
| Sustainability Compliance Documents (reference BDS 00 00 17 .1) | Including EUI, WUI, LCCA and Coordination with Cx and BECx requirements
Owner's Project Requirements (OPR)
| Program of Requirements (PoR) | ASF Database File
Design Review Board Presentation (if applicable)
BIM Requirements Statement (if required)
A/E Estimate in Excel format - reconciled with CMR estimate
CMR Estimate in excel format - reconciled with A/E estimate
Schedule
Basis of Design Narrative (BOD)
Any item not included on the drawings or in the submission require a comment. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
Pre-Design
Deliverable categories | Deliverables |  | Checkbox (X) | Comments
Site/Civil* | No Site/Civil Scope is needed in the project
Drawings and Specifications: adhere to indexing guidelines:
| Site Plan (based on OSU GIS map or surveyed map) | Tree Survey: identify tree species, tree canopy diameter & DBH
Zoning/easement/right of way confirmation
Design narrative
Utility capacity confirmation
OSU master plan confirmation
Any item not included on the drawings or in the submission require a comment. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
Pre-Design
Deliverable categories | Deliverables |  | Checkbox (X) | Comments
Architectural* | No Architectural Scope is needed in the project
Compilation of existing building drawings, information, and/or site photos anticipated to be relevant to the design and scope of the project.
| Narrative: | site improvements
circulation
organization of building space in relation to program requirements
building materials
special features
BECx plan
building systems (HVAC, plumbing, fire protection, structural, security, IT approach and video voice and data) & major equipment
Preliminary geotechnical information has been contracted
Any item not included on the drawings or in the submission require a comment. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
Pre-Design
Deliverable categories | Deliverables |  | Checkbox (X) | Comments
Structural* | No Structural Scope is needed in the project
Compilation of existing building drawings, information, and/or site photos anticipated to be relevant to the design and scope of the project.
| Structural Narrative (Renovations only): | Suggested exploratory demolition
Boring location markup & criteria for use of geotechnical consultant
Any item not included on the drawings or in the submission require a comment. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
Pre-Design
Deliverable categories | Deliverables |  | Checkbox (X) | Comments
HVAC* | No HVAC Scope is needed in the project
| See General submittal requirements | include Cx
Any item not included on the drawings or in the submission require a comment. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
Pre-Design
Deliverable categories | Deliverables |  | Checkbox (X) | Comments
Electrical* | No Electrical Scope is needed in the project
Narrative input on ERRS intent and design
Predictive modeling of an ERRS system
Baseline testing in existing buildings for design ERRS systems
Any item not included on the drawings or in the submission require a comment. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
Pre-Design
Deliverable categories | Deliverables |  | Checkbox (X) | Comments
Plumbing* | No Plumbing Scope is needed in the project
See General submittal requirements
Any item not included on the drawings or in the submission require a comment. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
Pre-Design
Deliverable categories | Deliverables |  | Checkbox (X) | Comments
Fire Protection* | No Fire Protection Scope is needed in the project
See General submittal requirements
Any item not included on the drawings or in the submission require a comment. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
Pre-Design
Deliverable categories | Deliverables |  | Checkbox (X) | Comments
Landscape* | No Landscape Scope is needed in the project
See General submittal requirements

## Schematic Design
DESIGN STAGE DELIVERABLE CHECKLIST
This checklist is intended to serve as a communication tool clarifying expectations of drawing content and submittal requirements at various stages to inform University Stakeholder's review of major design issues for practicality, aesthetics, sustainability, campus planning impacts and cost effectiveness. It is not a complete or exhaustive list of requirements and additional drawing information or submittals may be required based on individual project needs. Refer to the OSU Building Design Standards for complete requirements of the University. Minimum drawing requirements for the establishment of GMPs are to be coordinated between the DB/CMR and A/E based on contract requirements.
Any item not included on the drawings or in the submission require a comment response. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
SD Phase
Deliverable categories | Deliverables |  | Checkbox (X) | Comments/Responses
General | Updated Sustainability Applicability Matrix (SAM)
| Sustainability Compliance Documents (reference BDS 00 00 17 .1 ) | Including EUI, WUI, LCCA and Coordination with Cx and BECx requirements
Confirmed and updated OPR
Basis of Design Narrative (BOD)
| Confirmed and Updated Program of Requirements (PoR) | Updated ASF Database File : add column indicating change in ASF for each space
Code: Documentation of reviews with governing authority and/or consultant, show type and occupancy information
Zoning: Documentation of resolution of any zoning issues or variances from jurisdiction
Special Requirements: Documentation for resolution with special authorities for issues like the environment, historical limitations, utility services, etc
Geotechnical Report: Copy of site subsurface investigation report
| A/E Cost Estimate in Excel format: Reconciled with CMR estimate if applicable. Total project cost including but not limited to direct expenses, indirect expenses, land cost, and capital expenses | Direct Expenses: Construction, hazardous abatement, technology, contingencies.
Indirect Expenses: A/E fee, survey, geotechnical, permits, testing, reimbursables, project management, special inspections, utility connections, insurance, relocation expenses, etc.
Capital Expenses: Furnishings, equipment, contingencies.
Input from consultants on MEP, kitchen, civil work, etc.
| CMR Cost Estimate in Excel format: Reconciled with A/E estimate (if applicable). Total project cost including but not limited to direct expenses, indirect expenses, land cost, and capital expenses | Direct Expenses: Construction, hazardous abatement, technology, contingencies.
Indirect Expenses: A/E fee, survey, geotechnical, permits, testing, reimbursables, project management, special inspections, utility connections, insurance, relocation expenses, etc.
Capital Expenses: Furnishings, equipment, contingencies
Input from consultants on MEP, kitchen, civil work, etc.
Project Schedule: showing major milestones for the project, estimated project delivery date and phasing plan if appropriate
Documented approval of Schematic Design Stage by Owner
Design Review Board Presentation (if applicable)
Any item not included on the drawings or in the submission require a comment response. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
SD Phase
Deliverable categories | Deliverables |  | Checkbox (X) | Comments/Responses
Site/Civil* | No Site/Civil Scope is needed in the project
Drawings and Specifications: adhere to indexing guidelines:
| Topographic map | showing existing conditions, utilities, and other constraints such as easements
Site Plan
Landscape Plan
Any item not included on the drawings or in the submission require a comment response. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
SD Phase
Deliverable categories | Deliverables |  | Checkbox (X) | Comments/Responses
Architectural* | No Architectural Scope is needed in the project
Updated compilation of existing building drawings, information, and/or site photos anticipated to be relevant to the design and scope of the project.
| Updated Narrative: | site improvements
circulation
organization of building space in relation to program requirements
building materials
special features
building systems (HVAC, plumbing, fire protection, structural, security, IT approach and video voice and data) & major equipment
Drawings and Specifications: adhere to indexing guidelines:
| Primary elevations: | Scaled same as plan, noting principle materials
| Scaled building plan(s): including key plan and column lines | Indicate spatial relationships
Basic dimensions
Circulation areas
Doors and window openings
Location of fire rated elements
Identify each room or space with Program of Requirements Room Name and Item Number
Equipment and furniture layouts
| Preliminary building cross sections: | Through all floor and/or roof changes in elevation
selected to best show the relationships of architectural and engineering features
| List of alternate options for consideration by the Owner: | Include options that may affect the cost, quality, and/or schedule of the project
| Space planning of major or typical interior spaces: | Basic furniture
Fixtures
Equipment layout
Preliminary color schemes for discussion with the Owner
| BECx Plan outline | if required
| Outline specification: | Selection of building materials and systems
Any item not included on the drawings or in the submission require a comment response. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
SD Phase
Deliverable categories | Deliverables |  | Checkbox (X) | Comments/Responses
Structural* | No Structural Scope is needed in the project
Updated compilation of existing building drawings, information, and/or site photos anticipated to be relevant to the design and scope of the project.
| Structural Narrative: | Description of new or existing framing system and materials
Description of new or existing lateral resisting systems(s)
Description of anticipated foundation system
Identify any underground utilities or structures that may affect the foundation design
Identify considerations/investigations on adjacent structrures including potential effects of snow drift
| Renovations: | Identify changes in occupancy, use and/or new equipment that may result in changes to floor live load or dead load requirements. Provide preliminary sketch of areas of existing areas to be analyzed for new gravity loading.
Identify possible changes in applied lateral loads or the capacity of the existing lateral resisting system, including but not limited to additions, new screen walls, new RTU's, new openings in diaphrams or shear walls, changes to lateral load distribution and diaphragm effects or other modifications to the existing lateral system. Identify areas to be analyzed and discuss analysis methodology.
If retrofits are expected due to gravity or lateral modifications, describe anticipated strengthening methods
Indentify areas of deterioration that may require repair and description of anticipated repair methods
| Exploratory/Investigative Demolition documents for Renovations | In mark up form, in sufficient detail to contract necessary construction services
| Preliminary Design Data per OBC 1603.1: | Identify Risk Category
Identify anticipated wind loading procedure (ie envelope, directional or wind tunnel testing)
| Exceptions: | 1603.1.3 items 5 & 6
1603.1.4 item 5
1603.1.5 items 4-11 (if preliminary geotechnical report is available, provide as much information as possible)
1603.1.6
Typical Bay framing sketch with member sizes or typical reinforcing and dimensions
Any item not included on the drawings or in the submission require a comment response. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
SD Phase
Deliverable categories | Deliverables |  | Checkbox (X) | Comments/Responses
HVAC* | No HVAC Scope is needed in the project
Drawings: Adhere to indexing guidelines:
| Plans: including key plan and column lines | Building systems in diagrammatic form
Concurrence with sizes and location of mechanical rooms
Narrative input on basic systems description
Notes of consultations with public agencies and authorities on utility services and requirements
Input on basic clearances required for distribution systems
Cx/BECx Plan outline
CxP review of HELPT Narrative/BOD alignment to OPR
CxP review of SD Energy Model
CxP review of SD Water Model
BECx - Narrative of required testing, set up and process for air and/or water.
SD Energy Model
LCCA for SD Energy related options
Narrative of Thermal Comfort Strategies
Any item not included on the drawings or in the submission require a comment response. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
SD Phase
Deliverable categories | Deliverables |  | Checkbox (X) | Comments/Responses
Electrical* | No Electrical Scope is needed in the project
Drawings: Adhere to indexing guidelines:
| Plans: | Plans showing building systems in diagrammatic form
Concurrence with sizes and location of electrical rooms
Narrative input on basic systems description
Notes of consultations with public agencies and authorities on utility services and requirements
Input on basic clearances required for panels, fixtures, and distribution systems
Narrative input on ERRS intent and design
Predictive modeling of an ERRS system
Baseline testing in exisitng buildings for design ERRS systems
Any item not included on the drawings or in the submission require a comment response. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
SD Phase
Deliverable categories | Deliverables |  | Checkbox (X) | Comments/Responses
Plumbing* | No Plumbing Scope is needed in the project
Drawings: Adhere to indexing guidelines:
| Plans: including key plan and column lines | Building systems in diagrammatic form
Concurrence with sizes and location of mechanical rooms
Narrative input on basic systems description
Notes of consultations with public agencies and authorities on utility services and requirements
Input on basic clearances required for fixtures and distribution and drain systems
SD Water Model
LCCA for SD Water related options
Any item not included on the drawings or in the submission require a comment response. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
SD Phase
Deliverable categories | Deliverables |  | Checkbox (X) | Comments/Responses
Fire Protection* | No Fire Protection Scope is needed in the project
Drawings: Adhere to indexing guidelines
| Plans: including key plan and column lines | Building systems in diagrammatic form
Concurrence with sizes and location of mechanical rooms
Narrative input on basic systems description
Notes of consultations with public agencies and authorities on utility services and requirements
Input on basic clearances required for equipment
Any item not included on the drawings or in the submission require a comment response. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
SD Phase
Deliverable categories | Deliverables |  | Checkbox (X) | Comments/Responses
Landscape* | No Landscape Scope is needed in the project
See General submittal requirements

## Design Development
DESIGN STAGE DELIVERABLE CHECKLIST
This checklist is intended to serve as a communication tool clarifying expectations of drawing content and submittal requirements at various stages to inform University Stakeholder's review of major design issues for practicality, aesthetics, sustainability, campus planning impacts and cost effectiveness. It is not a complete or exhaustive list of requirements and additional drawing information or submittals may be required based on individual project needs. Refer to the OSU Building Design Standards for complete requirements of the University. Minimum drawing requirements for the establishment of GMPs are to be coordinated between the DB/CMR and A/E based on contract requirements.
Any item not included on the drawings or in the submission require a comment response. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
DD Phase
Deliverable categories | Deliverables |  | Checkbox (X) | Comments/Responses
General | Updated Sustainability Applicability Matrix (SAM)
| Sustainability Compliance Documents (reference BDS 00 00 18.1) | Including EUI, WUI, LCCA and Coordination with Cx and BECx requirements
Updated OPR if Scope Changes
Basis of Design (BOD) if Scope Changes
| Confirmed and Updated Program of Requirements (PoR) | Updated ASF Database File : add column indicating change in ASF for each space
Code: Documentation of reviews with governing authority and/or consultant, show type and occupancy information
Zoning: Documentation of resolution of any zoning issues or variances from jurisdiction
Special Requirements: Documentation for resolution with special authorities for issues like the environment, historical limitations, utility services, etc
| Cost Estimate in Excel format: A detailed estimate of the total project cost including but not limited to the following: | Direct expense: construction, hazardous abatement, technology, contingencies
Indirect expenses: A/E fees, survey, geotechnical, permits, testing, reimbursables, project management, special inspections, utility connections, insurance, moving expenses, etc.
Capital expense: furnishings, equipment, contingencies
Input from consultants on MEP, food service, civil work, etc
| CMR Cost Estimate in Excel format: Reconciled with A/E estimate: Total project cost including but not limited to direct expenses, indirect expenses, land cost, and capital expenses | Direct Expenses: Construction, hazardous abatement, technology, contingencies.
Indirect Expenses: A/E fee, survey, geotechnical, permits, testing, reimbursables, project management, special inspections, utility connections, insurance, relocation expenses, etc.
Capital Expenses: Furnishings, equipment, contingencies.
Input from consultants on MEP, kitchen, civil work, etc.
Any item not included on the drawings or in the submission require a comment response. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
DD Phase
Deliverable categories | Deliverables |  | Checkbox (X) | Comments/Responses
General | FF&E Budgets
CMR Constructability Review (if applicable)
| Site-specific Logistics Plan: | Temporary Facilities (trailers)
Temporary utilities requirements (temp electric requires permitting by ODIC)
Construction metering
Laydown and staging
Vehicular and pedestrian circulation for review by ENGIE, Operations and OSU Risk Management
Project Schedule: A schedule confirming major milestones for the project, estimated project delivery date, and phasing plan if appropriate
BIM model (projects > $4 million)
Any item not included on the drawings or in the submission require a comment response. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
DD Phase
Deliverable categories | Deliverables |  | Checkbox (X) | Comments/Responses
Site/Civil* | No Site/Civil Scope is needed in the project
Drawings and Specifications: adhere to indexing guidelines:
All previous design stage drawing requirements included in current submission
Topographic map
Site Plan
Landscape Plan
Irrigation Plan
Plan and Profile of Proposed Utilities
Roadway Profiles and Cross Sections
Grading Plan
MOT Plan
Stormwater Calculations
Pavement Caculations
Any item not included on the drawings or in the submission require a comment response. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
DD Phase
Deliverable categories | Deliverables |  | Checkbox (X) | Comments/Responses
Architectural* | No Architectural Scope is needed in the project
Updated compilation of existing building drawings, information, and/or site photos anticipated to be relevant to the design and scope of the project.
Drawings and Specifications: adhere to indexing guidelines:
All Pre-Design & SD drawing requirements
| Scaled building plan(s): including key plan and column lines | Dimensions
Location of fire rated elements
Wall thicknesses
Ingress and egress locations
Door swings with numbers
Casework/millwork
Equipment
Fixture locations
Assigned Room numbers
Room Names
Vertical pipe and duct spaces
Structural columns
Include Program of Requirements Item Numbers
| Schedules: if sheet size is sufficient, include on the associated floor plan sheet: | Ceiling finshes
Wall finishes
| Reflected ceiling plans : | Ceiling heights
Any item not included on the drawings or in the submission require a comment response. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
DD Phase
Deliverable categories | Deliverables |  | Checkbox (X) | Comments/Responses
Architectural* | Roof Plan(s): | Principal mechanical items
Principal electrical items
Slopes
Key reference roofing high point
Valley and drain elevations (altitudes referenced to project benchmark)
Roof drains
Penetrations
Walkways
Large piping
Air ducts
Fans
Condensers
Roof structures
Equipment screens
Ladders
Fall protection
Lightning protection
Green rooftop solar
Blue roof considerations
Plaza
Any item not included on the drawings or in the submission require a comment response. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
DD Phase
Deliverable categories | Deliverables |  | Checkbox (X) | Comments/Responses
Architectural* | Elevations: | Drawn to same scale as plans
Dimensions of all basic design features (grade/windows/fascias/brick patterns/mechanical screens/louvers/etc.)
Fresh air intake louvers clearly identified
Floor and roof lines
Grade lines and footings
Everything exposed to view above eaves or parapets
| Building cross sections and primary wall sections: | Further developed for all change in floor levels and wall conditions
| Enlarged plans of key areas: | Furniture and equipments layouts
Any floor wall or ceiling treatments
Mechanical equipment room layouts for required clearances
Kitchen area
| Finish Schedule: | For all spaces
| Opening schedule: | Sizes
Materials
Fire ratings
Special construction (i.e. sound isolation)
| Wall sections and typical construction details: | For the various conditions
| Sections: | Delineating special features such as stage equipment, acoustical treatments, etc
Symbol legend
Scaled plans showing furniture and equipment
Preliminary selections for furniture and equipment
Color schemes/patterns for major finish elements
| Outline specifications: | All building materials and systems indicating a minimum of 3 acceptable manufacturers and/or suppliers
Front end specification items covering bidding requirements, special project conditions, phasing of the work, allowances, unit prices, alternates, etc.
Any item not included on the drawings or in the submission require a comment response. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
DD Phase
Deliverable categories | Deliverables |  | Checkbox (X) | Comments/Responses
Structural* | No Structural Scope is needed in the project
Updated compilation of existing building drawings, information, and/or site photos anticipated to be relevant to the design and scope of the project.
Drawings: Adhere to indexing guidelines:
All previous design stage drawing requirements included in current submission
| Outline General Notes: | Do not include unedited notes or scope not pertaining to the project.
| Foundation plan: including key plan and column lines | Drawn same scale as Architectural plan
Floor elevations
Footing elevations
Typical details
Special conditions
Slab thicknesses
Key Plan and North Arrow
Any underground utilites or structures that affect the foundation design
Show adjacent/abutting existing foundations
| Framing plans same scale as architectural plans for each level and roof: including key plan and column lines | Dimensions
Locations and sizes of primary structural members
principal top of framing elevations
Key Plan and North Arrow
Floor Live Loads
Location of building expansion joints
Typical sections and details
| Updated Design Criteria: | Include snow drift values per OBC 1603.1.3
Identify wind loading procedure (ie envelope, directional or wind tunnel testing)
Exception:1603.1.4 item 5
Any item not included on the drawings or in the submission require a comment response. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
DD Phase
Deliverable categories | Deliverables |  | Checkbox (X) | Comments/Responses
Structural* | Signed Sealed Letter- for renovations that will not require structural drawings to show new elements or retrofit of existing elements (typically 1-2 pages in length): | Reference to OSU project number (if applicable)
Description of new loads or specific equipment including pertinent information such as load type & code references, weight, size, and anchor bolt patterns, etc. Referencing and attaching equipment cut sheets with the above pertinent information highlighted is also acceptable
Description of assumptions/known information regarding the existing structure/foundation being evaluated including information critical to analysis (ie slab/pad thickness, reinforcing critical to capacity, assumed bearing capacity etc.)
Reference existing drawing sheets upon which analysis was based, including OSU project number, sheet names and drawing dates and/or attach individual sheets (not entire drawing sets) pertient to analysis for reference
Brief description of analysis performed including applicable failure mechanisms evaluated
Statement of adequacy of existing structure to safely support new loads or recommendation to be retrofit/ alternate solution pursued
Signature and seal with date by engineer licensed in Ohio
| Outline specifications: | Minimum of 3 acceptable manufacturers
Calculations to analyze and check the load carrying capacities of various structural members (upon request)
Any item not included on the drawings or in the submission require a comment response. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
DD Phase
Deliverable categories | Deliverables |  | Checkbox (X) | Comments/Responses
HVAC* | No HVAC Scope is needed in the project
Drawings: Adhere to indexing guidelines:
All previous design stage drawing requirements included in current submission
| Floor plan(s): including key plan and column lines | Drawn same scale as architectural plans
distribution systems - duct and piping shown
equipment locations (with maintenance clearances indicated)
Show all piping, ductwork and equipment sizes, required clearances and weights
Show locations of all accessories such as diffusers, dampers, louvers, thermostats, etc
Major structural penetrations and loads coordinated with structural
Symbol legend
| Enlarged plan of mechanical equipment rooms | Show equipment layouts (with maintenance clearances)
| Roof Plan(s): | Details of equipment (size and weight, ect.)
| Ground mounted equipment | Details of equipment (size and weight, etc.)
Acoustical treatment recommendations where necessary
| HVAC system major design calculations as required | note all assumed design criteria - not all calculations noted in checklist
| Heating and cooling load calculations for each individual space | note all assumed design criteria - not all calculations noted in checklist
| Ventilation Calc for each space and asoociated HVAC equpiment | note all assumed design criteria - not all calculations noted in checklist
Any item not included on the drawings or in the submission require a comment response. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
DD Phase
Deliverable categories | Deliverables |  | Checkbox (X) | Comments/Responses
HVAC* | Thermal stress analysis for steam, condensate, HHW, & CHW pipng per ASME B31.1 Power Ping Design and Fabriacation and OBC Pressure ping Systems Code with Isometric/ pipe lengths node location identifiers | note all assumed design criteria, pipe material selection, diameter and schedule. Results shall show different modes of operation: pressure, P&T, P,T& weight, and cold and hot pipe configurations as needed
| HVAC schematic one-line flow diagrams | for air, hydydronic and steam systems; to clarify system design intent. Ie - steam piping diagram provided with pressures, temp, valve Cv ratings, relief valve settings, pressure gauges and thermometers, etc.
| Equipment schedules | Indicate size and capacity
| Outline specifications | Minimum of 3 acceptable manufacturers
Cx/BECx Full Plan
| CxP review of updated HELPT Narrative/BOD alignment to OPR | Coordinate updated SAM (HVAC, Electrical, Plumbing, Lighting, Technology)
CxP review of DD Energy Model
CxP review of DD Water Model
Update BECx Plan following 100% DD energy modeling.
Deliver results of review and issues log.
DD Energy Model
LCCA for DD Energy related options if requested.
Complete CBE Thermal Comfort Tool for Analysis
Define space types and perform ventilation calculations
Any item not included on the drawings or in the submission require a comment response. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
DD Phase
Deliverable categories | Deliverables |  | Checkbox (X) | Comments/Responses
Electrical* | No Electrical Scope is needed in the project
Drawings: Adhere to indexing guidelines:
All previous design stage drawing requirements included in current submission
| Site Plan: | Drawn same scale as architectural plans
Site lighting - Light pole placement, photometric study
Building exterior lighting - fixture placement, photometric study (account for nearby site lighting as appropriate)
Utility service
Utility connections
Power to other outdoor facilities such as athletic facilities, signs, etc.
| Floor Plan (s): including key plan and column lines | Drawn same scale as architectural plans
Distribution systems (i.e. transformers, switch gear, panelboards, etc.)
Lighting
Power
Power consuming equipment locations with preliminary camera locations and access control facilities clearly identified
Symbol legend
| Schedules: showing electrical characteristics, design loads, capacities, etc. as appropriate | Fixtures
Panels
Equipment
Food service equipment
| Outline specifications | Minimum of 3 acceptable manufacturers
| ERRS system | Single-line riser wiring diagram
Schematic and detail drawings of the proposed system architecture indicating proposed locations for system components
Any item not included on the drawings or in the submission require a comment response. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
DD Phase
Deliverable categories | Deliverables |  | Checkbox (X) | Comments/Responses
Plumbing* | No Plumbing Scope is needed in the project
Drawings: Adhere to indexing guidelines:
All previous design stage drawing requirements included in current submission
| Plumbing system major design calculations as required | note all assumed design criteria
| Floor plan(s): including key plan and column lines | Water
Sanitary waste
Compressed air
Acid waste
Special traps (i.e. plaster, grease)
Gas piping with sizes
Location of all fixtures
Show meter locations, sizes
Connections to storm water system
Symbol legend
| Roof Plan(s) | Roof drainage system
Plumbing fixture schedule
| Outline specifications | Minimum of 3 acceptable manufacturers
DD Water Model
LCCA for DD Water related options
Any item not included on the drawings or in the submission require a comment response. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
DD Phase
Deliverable categories | Deliverables |  | Checkbox (X) | Comments/Responses
Fire Protection* | No Fire Protection Scope is needed in the project
Drawings: Adhere to indexing guidelines:
All previous design stage drawing requirements included in current submission
| Floor plan(s) including key plan and column lines | Hazard classifications
Fire protection piping
Devices
Valve locations
Equipment locations
Symbol legend
| Outline specifications | Minimum of 3 acceptable manufacturers
Any item not included on the drawings or in the submission require a comment response. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
DD Phase
Deliverable categories | Deliverables |  | Checkbox (X) | Comments/Responses
Landscape* | No Landscape Scope is needed in the project
Drawings: Adhere to indexing guidelines:
All previous design stage drawing requirements included in current submission
| Site Landscaping Development Plan: | ADA
Details
Grading
Landscape features
Retaining walls
Site furnishings
Bike Parking
Note on C230: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Destadio, Michael - added with Steve - for your review Reply: Thanks Carrie - we may want to add "building exterior lighting placement" as well after light poles as that will affect the photometrics when applicable
Note on C231: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Destadio, Michael - is this the correct location? if not feel free to modify as appropriate @Volkmann, Stephen Reply: *edited

## Construction Documents
DESIGN STAGE DELIVERABLE CHECKLIST
This checklist is intended to serve as a communication tool clarifying expectations of drawing content and submittal requirements at various stages to inform University Stakeholder's review of major design issues for practicality, aesthetics, sustainability, campus planning impacts and cost effectiveness. It is not a complete or exhaustive list of requirements and additional drawing information or submittals may be required based on individual project needs. Refer to the OSU Building Design Standards for complete requirements of the University. Minimum drawing requirements for the establishment of GMPs are to be coordinated between the DB/CMR and A/E based on contract requirements.
Any item not included on the drawings or in the submission require a comment response. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
CD Phase
Deliverable categories | Deliverables |  | Checkbox (X) | Comments/Responses
General | Updated Sustainability Applicability Matrix (SAM)
| Sustainability Compliance Documents (reference BDS 00 00 19.1 & SAM) | Including EUI, WUI, LCCA and Coordination with Cx and BECx requirements
Updated OPR if Scope Changes
Basis of Design (BOD) if Scope Changes
| Confirmed and Updated Program of Requirements (PoR) | Updated ASF Database File : add column indicating change in ASF for each space
| Cost Estimate in Excel format: A detailed estimate of the total project cost including but not limited to the following | Direct expense: construction, hazardous abatement, technology, contingencies
Indirect expenses: A/E fees, survey, geotechnical, permits, testing, reimbursables, project management, special inspections, utility connections, insurance, moving expenses, etc.
Capital expense: furnishings, equipment, contingencies
Input from consultants on MEP, food service, civil work, etc
| CMR Cost Estimate in Excel format: Reconciled with A/E estimate. Total project cost including but not limited to direct expenses, indirect expenses, land cost, and capital expenses | Direct Expenses: Construction, hazardous abatement, technology, contingencies.
Indirect Expenses: A/E fee, survey, geotechnical, permits, testing, reimbursables, project management, special inspections, utility connections, insurance, relocation expenses, etc.
Capital Expenses: Furnishings, equipment, contingencies.
Input from consultants on MEP, kitchen, civil work, etc.
Construction schedule
Permits
CMR or DB Constructability Review (if applicable)
Furniture Estimate
Commissioning and Sustainability Review
Final Energy Model
| Updated LCCA (if requested) | Energy, water and/or materials
BIM model (projects > $4 million)
Any item not included on the drawings or in the submission require a comment response. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
CD Phase
Deliverable categories | Deliverables |  | Checkbox (X) | Comments/Responses
Site/Civil* | No Site/Civil Scope is needed in the project
Drawings and Specifications: adhere to indexing guidelines:
All previous design stage drawing requirements included in current submission
Topographic map
Site Plan
Landscape Plan
Irrigation Plan
Plan and Profile of Proposed Utilities
Road Cross Sections
Grading Plan
Details
MOT Plan
Easement Plan
Stormwater Calculations
Pavement Caculations
Any item not included on the drawings or in the submission require a comment response. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
CD Phase
Deliverable categories | Deliverables |  | Checkbox (X) | Comments/Responses
Architectural* | No Architectural Scope is needed in the project
Updated compilation of existing building drawings, information, and/or site photos anticipated to be relevant to the design and scope of the project.
Drawings and Specifications: adhere to indexing guidelines:
All previous design stage drawing requirements included in current submission
Code Information/Data
Survey
Site Plan
| Floor Plan(s): including key plan and column lines | Each level including mechanical mezzanines
Enlarged Plans – special areas
Building Elevations
Building Cross Sections
Building Wall Sections
Stair and Elevator Sections
Special details
Interior finish details
Room Finish Schedule
Door, Frame, and Hardware Schedule
Furniture/ Equipment/ Casework Plans/ Elevations/ Details
Special Construction Plans/Details (Pools/Auditoriums/etc)
Sequence of the Work Plan (Phasing)
Cx/BECx Full Plan
Project Manual:
| Complete Standard Requirements (Division 00): | Table of Contents
Solicitation
Instructions to Bidders (include Supplementary Instructions if applicable)
Bid Form
Bid Security Form
Bidder’s Qualifications
EDGE Affidavit
Contract Form
Performance and Payment Bond Form
Contracting Definitions
General Conditions (include Supplementary Conditions if applicable)
Wage Rate Requirements
Complete General Requirements Specification (Division 01)
Complete Technical Specifications (Divisions 02 thorough 49)
Any item not included on the drawings or in the submission require a comment response. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
CD Phase
Deliverable categories | Deliverables |  | Checkbox (X) | Comments/Responses
Structural* | No Structural Scope is needed in the project
Updated compilation of existing building drawings, information, and/or site photos anticipated to be relevant to the design and scope of the project.
Drawings: Adhere to indexing guidelines:
All previous design stage drawing requirements included in current submission
| Complete General Notes: | For steel projects, specifically state which option(s) from AISC COSP are being utilized for connection design.
Indicate all delegated design items including but not limited to steel connections, cold formed metal framing, misc steel such as stairs, trusses ect
Complete Foundation Plan: including key plan and column lines
| Complete Framing Plans: including key plan and column lines | show equipment outlines with basis of design operating weights
Typical details
| Special details | Control/Contraction/Expansion joint locations in either plan or elevation for concrete or CMU walls
Structural Schedules (columns, lintels, etc.)
| Complete Design criteria: | Include snow drift values per OBC 1603.1.3
Include graphic indicating "a" (or 0.6h) dimensions for wind loading zone applicablility including clear identification at "bump-outs", horizontal steps at elevation changes, and angles less than 135 degrees (reference ASCE 7-16 C30.3.2)
Coordinate Technical Specifications (Divisions 02 thorough 49)
Calculations to analyze and check the load carrying capacities of various structural members (upon request)
Any item not included on the drawings or in the submission require a comment response. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
CD Phase
Deliverable categories | Deliverables |  | Checkbox (X) | Comments/Responses
HVAC* | No HVAC Scope is needed in the project
Drawings: Adhere to indexing guidelines
All previous design stage drawing requirements included in current submission
Site Plan(s)
Floor Plans key plan and column lines
| Detailed Equipment Room Plans | clearances shown; valve chart indicated
Detailed Equipment Room Sections
| Special details | as required, including steam piping diagram with pressures, temp, ratings, seetings guages, etc.
| Ventilation caluclations | Final calcs and thermal comfort
Equipment and Fixture Schedules
Technical Specifications Divisions 23 and 25
Cx/BECx Full Plan
CxP review of updated HELPT Narrative/BOD alignment to OPR
CxP review of CD Energy Model
| CxP review of CD Water Model | include reasoning for data inputs
Update BECx Plan following 100% CD energy modeling.
Deliver results of review and issues log.
| CD Energy Model | include anticipated EUI performance
LCCA for CD Energy related options if requested.
Performance and Verification Benchmarking
Any item not included on the drawings or in the submission require a comment response. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
CD Phase
Deliverable categories | Deliverables |  | Checkbox (X) | Comments/Responses
Electrical* | No Electrical Scope is needed in the project
Drawings: Adhere to indexing guidelines:
All previous design stage drawing requirements included in current submission
Site Plan(s)
Floor Plans: including key plan and column lines
| Detailed Equipment Room Plans | circuitry and lighting controls
Detailed Equipment Room Sections
Special details
Equipment and Fixture Schedules
Fire Detection Equipment
Coordinate Technical Specifications (Divisions 02 thorough 49)
| ERRS system | Updated single-line riser wiring diagram
Updated schematic and detail drawings of the proposed system architecture indicating proposed locations for system components
| ERRS | Specifications for procurement and installation of a complete system with required permits and submittals for review by AHJ as well as OSU
Any item not included on the drawings or in the submission require a comment response. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
CD Phase
Deliverable categories | Deliverables |  | Checkbox (X) | Comments/Responses
Plumbing* | No Plumbing Scope is needed in the project
Drawings: Adhere to indexing guidelines:
All previous design stage drawing requirements included in current submission
Site Plan(s)
Floor Plans: including key plan and column lines
| Detailed Equipment Room Plans | clearances shown; valve chart indicated
Detailed Equipment Room Sections
Special details
Equipment and Fixture Schedules
Coordinate Technical Specification Division 22
CD Water Model
LCCA for CD Water related options
Any item not included on the drawings or in the submission require a comment response. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
CD Phase
Deliverable categories | Deliverables |  | Checkbox (X) | Comments/Responses
Fire Protection* | No Fire Protection Scope is needed in the project
Drawings: Adhere to indexing guidelines:
All previous design stage drawing requirements included in current submission
Site Plan(s)
Floor Plans: including key plan and column lines
Detailed Equipment Room Plans
Detailed Equipment Room Sections
Special details
Equipment Schedules
Coordinate Technical Specifications Division 21
Any item not included on the drawings or in the submission require a comment response. This includes items not included on the basis of project scope (i.e. N/A - not in project scope)
* See also General Deliverable Category for additional submittals requiring input of each discipline
CD Phase
Deliverable categories | Deliverables |  | Checkbox (X) | Comments/Responses
Landscape* | No Landscape Scope is needed in the project
Drawings: Adhere to indexing guidelines:
All previous design stage drawing requirements included in current submission
Complete Site Landscaping Development Plan