## Risk Management Overview
Overview
Facilities Operations and Development (FOD) is responsible to minimize risks inherent to capital construction projects. Construction risks can be minimized by identifying and rating risk severity and developing mitigation plans for those risks deemed to be of moderate or high risk potential.
This guideline applies only to managing risks during construction. For addressing risks associated with building operations or utility outages after occupancy, please reference the file “What if Risk Assessment for Utility System Changes” located at https://fod.osu.edu/resources under the “Utilities” tab.
Process
Step 1. Initial Risk Identification (pre-design) The Project Manager is responsible to complete the initial risk identification for construction projects. This is a high level review to determine whether additional investigation is warranted during design. The OSU GIS and/or underground maps along with the TSG representative and the Utilities Division should be consulted in this initial identification.
A) Identify underground infrastructure within the project impact area
B) Evaluate construction impacts to pedestrian, bicycle and vehicle safety.
C) Consult Utility Authority Having Jurisdiction (AHJ) (ENGIE or other utility owner), TSG representative, OCIO, Mapping, Student Life, and DoP (as necessary) to complete initial assessment
D) Determine whether an additional service is warranted and should be included in A/E scope of services. Review the questions outlined in Attachment #1. Include in Criteria A/E, D/B, and CMR scopes as appropriate for alternative project delivery methods.
Step 2. Technical Service Scope Development. Develop scope to be included in the A/E of record’s scope for Risk Identification and Risk Mitigation Plan.
A) For traditional Design, Bid, Build projects, include as an additional service for the A/E.
B) For CMR or CM as agent include scope in the A/E (additional service) and CM preconstruction services scope
C) For Design Build, include scope in the Criteria A/E, and the DB contract
Step 3. Risk Assessment @ SD/DD As warranted by step 1, the designer of record will determine specific risks and develop additional details during the early design phases of the project.
A) Identify & locate utilities within the project impact area
B) Review effects of any incident on surrounding operations.
C) Address pedestrian and traffic management, equipment delivery and laydown, cranes and construction equipment movement.
D) Consult the utility owner/AHJ, TSG representative, OCIO, Mapping and DoP (as necessary) to complete assessment
E) Should directional boring be included as a viable construction technique, additional requirements for reviewing utility marking and hydro-excavation or other nondestructive location of utilities within the path of the bore shall be reviewed. The utility marking and locating requirements will be developed in section F. IV below.
F) Determine the level of mitigation necessary for this project to be included in the CD plans. The intention of the requirements below is that they are cumulative. Example: if a project requires activities identified in number IV below, the activities in II and III are required as well. Determinations are to be made in consultation with the Jurisdiction Having Authority, Office of Risk Management and others as appropriate.
I.) No action. Normal project delivery practices are adequate to mitigate risk to University assets.
II.) Enhanced Emergency Call List. Develop an enhanced call list to include phone trees specific to the affected asset. See attachment #2 for a template
III.) Utility shut off plan. For those utilities with key shut off valves, plans are to identify the location of the nearest valve. Plans are to be included in the CD drawings with instructions to the contractor to keep drawings on file and up to date throughout the project. Red line updates to the shut off plan are required following any phased startup of new utility systems. Key shutoff valves must remain accessible during construction.
IV.) Enhanced Excavation permit and other requirements. Markings are required as outlined in the Construction Supplemental Conditions without regard to the requirements of this section. Where sufficient risk is identified, the project team is to develop an enhanced excavation and/or directional bore permit process. At minimum, the contractor (incl. DB & CMR) and A/E of record are to sign off on the permit. (See attachment #3 for an example)
V.) Stock repair parts. Work with the project team to determine what repair parts are to be kept on site due to the nature of the project risk.
Step 4. Risk Management Plan during CD development. The team is to develop the Risk Mitigation plan required by Step #3 during CD development and complete it prior to start of construction. In situations where start of construction precedes full CD completion (as in the case of Design Build or other fast track project sequencing), the Risk Management Plan must be approved prior to start of construction. .
Step 5. Approval of Risk Management Plan. The plan will be submitted with the CD plans for review and approval by the various affected departments. Contractor requirements shall be included in Division 01 73 00 of the project specifications. In the case where the project start of construction precedes the submission of CDs, the plan will be routed and approved via a separate submission that follows typical plan submittal processes. Approvals for plans under implementation prior to full CD development will require signatures from the AHJ of each affected utility. For pedestrian and traffic management plans, signatures from TTM will be required. All plans will be provided to the Office of Risk Management one week prior to the start of construction.
Step 6. Risk Managment Plan - Construction The Risk Management Plan is to be implemented, verified, and updated on a regular basis throughout the construction of the project.
A) Conduct Utility Impact Pre-planning meeting (periodic meetings to focus on descrete construction limits may be preferred to a single meeting)
I. Review utilities impacted by construction
II Review Emergency Call lists and update contacts as needed
III Revew utility shut off notice requirements and timing
IV Review transition areas (outside of planned dig area but in proximity)
a. Review utilites outside of dig limits (assess impacts if utility is marked incorrectly - consider hydro excavating utilities adjacent to dig area)
V.) Assess whether any utilies within dig area should be de-energized
VI.) Identify all utilities to be pot-holed and contractor to identify methods to be used
B) Weekly Progress Meetings. An agenda item is to be included in the agenda and utilized to address issues related to the Mitigation Plan
I.) Verify the Plan is being followed
II.) Incidents where the Plan was implemented
III.) Upcoming work that is covered by the Plan
IV.) Discuss any areas where potholing was unsuccessful in locating utility or did not match OUPS markings
a. Call OUPS for remark of utility
b. If Utility not located - Utility owner, University, Contractor, and AE to meet to determine next steps. Decision should be colaborative and involve all parties
IV.) Updates to the Plan (ex: updates to call lists or Utility Shut Off Plan)
C) Schedule periodic meetings to review the Response Plan as construction progress, bulletins, and means & methods may require changes to the plan. The project team shall meet as required to review the Risk Mitigation Plan
I.) Review effectiveness of the Plan
II.) Verify adherence to the Plan –determine corrective actions and follow up
III.) Determine whether adjustments to the Plan are warranted.
Step 7. After Action Reports. After action reports are to be completed when an incident occurs. An analysis of the Response Plan is to be included as part of the report and appropriate updates implemented.
Resources
For information, consultation, and support:
FDC ~ Glen Yoder yoder.237@osu.edu

## Questionaire
Attachment #1
Preliminary Construction Risk Assessment Questionnaire
To be utilized at the beginning of a project to determine whether additional actions are needed.
Project Name:
Project Number:
Date:
Feature | Question | Further action required?
General
Are the OSU underground systems located by detailed survey or less specific means?
Are there Public Utilities (water, gas, electric) in the area that need OUPS Marking?
Are underground service lines at risk from directional boring or core sampling?
Will construction dust, noise or vibration impact adjacent buildings?
Will the project require multiple construction sequences and partial utility startups?
Water lines
Are there domestic waterlines within the work area?
Are there irrigation water lines within the work area?
Will there be an increased risk of freezing waterlines during construction (will cover be reduced)?
Will there be planned building outages?
What buildings are fed from the waterlines within the work area?
In the event of a water line break…..
Are there adjacent buildings or other critical features that may be damaged?
Has the unplanned loss of fire water and fire protection systems been considered?
Would the water migrate to a tunnel, trenchbox or other underground conduit?
Are critical water shutoff valves accessible, been tested or are known to leak through?
Electrical
Are there any electrical distribution duct banks within the project area?
Are there buried traffic lights or campus lighting circuits in the area?
What buildings or electrical equipment is served?
Are there any ongoing critical activities within the buildings potentially affected by the project?
Is any directional boring planned and are special precautions needed to protect critical circuits?
Natural Gas
Are there any distribution gas lines within the project area?
What buildings do they serve?
In the event of a gas line damage and leak?
Are there any ongoing critical activities (winter heating, food service) within the buildings potentially affected by the project if there is an unplanned gas outage?
Are there adjacent building air intakes that could be impacted by a gas leak?
Are critical gas shutoff valves accessible and operable?
OCIO
Are there any OCIO duct banks within the project area?
What buildings/servers/switches would be affected if the duct bank were damaged?
Steam & Condensate
Are there any steam and condensate lines within the project area?
Are there any planned outages?
What buildings would be affected by an outage (planned or unplanned)?
Are there any ongoing critical activities within the buildings potentially affected by the project?
Are critical steam shutoff valves accessible, been tested or are known to leak through?
Chilled Water
Are there any chilled water lines within the project area?
Are there any planned outages?
What buildings would be affected by an outage (planned or unplanned)?
Are there any ongoing critical activities within the buildings potentially affected by the project?
Have critical water shutoff valves been tested or are known to leak through?
Tunnels/Trenchboxes
Are there any tunnels or trenchboxes in the vicinity of the area?
Will the project be re-routing surface drainage that might impact the tunnel?
Could water from a water line break or storm drainage enter a tunnel or trenchbox?
Will construction vehicles or new roads impact existing tunnels?
Pedestrian
What is the likely access point to the project site?
Is the project in a heavy pedestrian area?
Are there any unique equipment or delivery methods of added risk to pedestrians?

## Excavation Permit
Appendix A - Excavation Permit
Project No. |  |  |  | Contractor Company Name
Project Name:
Phase I |  |  |  | Date Submitted
A completed dig permit must be submitted 24 hours prior to the start of work which calls for penetrating the soil either by digging methods or driving objects into the ground more than twelve inches. No work shall commence until the contractor receives this SIGNED dig permit from the AE. Permit is vaild for up to 30 days, but must be renewed weekly. IT WILL BE GROUNDS FOR DISMISSAL IF THE OPERATOR DOES NOT HAVE POSSESSION OF THIS PERMIT DURING SOIL PENETRATION.
Date work is to begin |  |  |  | Contractor Supt/Foreman |  | PH#:
Date work is to complete |  |  |  | Operator |  | AE Signature
Permit Expires |  |  |  | Weekly Renewal Due By |  | _______________
_______________
_______________
| Phone | Yes | No | Comments | Signatures | Company
White excavation marking performed per ORC
Physical Marking of all known utilities
OUPS
OCIO | 292-2202
JHA:
JHA:
Hydroexcavation of all existing known utilities within excavation and 24" beyond the excavation
Contract drawings reviewed and attached with excavation limits clearly identified
Contractors shall explain the work to be completed, including methods of soil penetration: (ex. Using a backhoe; ACME Contractor will be digging a trench ~ length, ~ width and ~ depth, to lay a run of pipe to tie into an existing water line. Work is expected to take place approximately 2-4 hours with a total of 4 workers, one of which is the competent person. The trench will be backfilled when completed.)
Contractor shall state the type of trench or excavation protection they plan to use for the soil conditions and what procedures will be followed within 18" of a utility: (ex. ACME Contractor will be sloping soil at a 1:1 slope per identified Type B Soil, with ladder access placed a maximum of 25 feet from work in either direction. Shovels will be used when excavating within 18" of a utility.)
Competent Person identified that will be present during excavation (note name in the comments)
Demolition drawings reviewed
Civil drawings reviewed, including all utility drawings
Structural drawings reviewed
Electrical drawings reviewed
Mechanical drawings reviewed
Project as-built drawings reviewed to verify no additional utilities in the area
Walk the site and ensure all known and shown utilities have been marked
Walk site and review all utilities that could be affected
Field verify all utility shut off locations (for utilities that could be affected), refer to Risk Mitigation Plan
DISCLAIMER: |  |  |  | PERMIT SIGN OFF Contractor Rep
Sign-off of this Permit does not release the Contractor from responsibilities contained within the Contract Documents nor does it shift responsibilities to the AE or the Owner. |  |  |  | AE Rep
ENGIE Rep
JHA Rep
JHA Rep

## Example Enhanced Call List
Ohio State University *Project* Disaster Recovery Plan
ELECTRICAL
In Case of Emergency Dial 911
Primary Call Order | Department / Secondary Call Order | Name | Work Phone | Cell Phone | Email | Action
1 | Service2Facilities |  | 614.292.6158 | 614.292.6158 | n/a | Notify Department
2 | Send Mass Notification Email
3 | Student Life Security |  |  |  |  | Notify Department
OSUWMC Security
4 | ENGIE Assessment Team
| 1 |  |  |  |  | Notify Department / FOD Assesment Team Members
| 2 | ENGIE PM
| 3 | Roger Music | 614.292.6272 | 614.216.9532 | music.16@osu.edu
4
5 | FOD PM/CM Team
| 1 | OSU PM- |  |  |  | Notify FOD PM/CM Team Members
| 2 | OSU CM-
| 3 | OSU DoP
| 4 | FDC Desk
5
6 | Localized Blackout Team
| 1 | Jeffrey Buckler | 614.292.6273 | n/a | buckler.6@osu.edu | Notify Department / Blackout Team Members
| 2 | Robert felty | 614.292.6274 | n/a | felty.1@osu.edu
| 3 | Randy Strode | 614.292.6275 | n/a | strode.7@osu.edu
| 4 | Jon Taylor | 614.292.6276 | n/a | taylor.259@osu.edu
7 | Emergency Mgmt & Fire Prev.
|  | Robert Armstrong | 614.247.4276 | 614.247.4276 | armstrong.349@osu.edu | Notify Department
8 | OSU Police
|  |  | 614.292.2121 | 614.688.3742 |  | Notify Department
9 | Contractor Staff
Infrastructure & Roadways
| 1 |  |  |  |  | Notify Contractor Staff / Safety Representatives
2
3
4
1
2
3
| PROJECT Contractor Specific |  | See Reference Sheet in Tab 7
10
| 1 |  |  |  |  | Notify Department
2
3
11 | Student Life Staff
Notify Department
12 | Dept of Public Safety
|  |  | 614.292.7677 | 614.247.6300 |  | Notify Department
13 | TTM
|  | Marshall King | 614.292.9341 | 614.563-0684 | king.414@osu.edu | Notify Department
14 | Environmental Health & Safety
|  | Thomas Novotny | 614.688.1764 |  | novotny.66@osu.edu | Notify Department
15 | Student Life Emergency Mgt.
|  | Jim Thomas |  |  | thomas.1714@osu.edu | Notify Department
Electrical Materials List Stored at XXXXXX down area trailer #XXXX (Example)
3000 feet---500KCM 15KV cable per OSU requirements in Division 33 of the specs
3000 feet---4/0 15KV cable per OSU requirements in Division 33 of the specs
2000 feet---4/0 green 600 volt THHN cable per OSU requirements in Division 33 of specs
12 ea. --- Raychem HVS-1533-LC
12 ea. --- Raychem HVSY-1523S
12 ea. --- Raychem HVSH-1523-MOD
Electrical - FOD Assessment Team Task Assignments
1. Identifies ION system to view graphical information as to the nature of the failure. Based on data in the system, can typically pinpoint the location of the failure. Physically inspect the failure.
2. Depending on the size and cause of the outage, contact the appropriate team for resolution of the outage.
3. Contact service center to start communications. Notify the Service Center of the situation so communications can begin. If possible, include estimated outage time for OSU buildings.
Electrical - Localized Blackout Team Task Assignments
1. Assess the damage (high voltage team) to the electrical system
2. Determine if isolation of the failure is possible
3. Notify the FOD Service Center of the situation and remediation schedule if possible. Provide as much information as possible.
4. Proceed with Isolation (if possible). Shift the system around to bypass the failure or cut and cap.
5. Determine steps and materials necessary for repair. OSU staff can make minor repairs but major repairs will be contracted with outside vendor(s). May require electrical contractors, welders, etc.
6. Gather materials and labor to perform repairs. OSU staff can make minor repairs but major repairs will be contracted with outside vendor(s). May require electrical contractors, welders, etc.
7. Call contractors (if necessary). Determine which contractors are needed, if any , to fix the problem.
8. Rotate buildings to alternate circuit. Every building has two circuits; except those in the Fisher College of Business, which have two circuits into their switching station but only one feeder coming out the other side to those buildings.
9. Contact service center with intermediate report. Keep the Service Center updates on the status of the outage and repairs.
10. Make repairs. Make the necessary repairs to bring electricity back to the affected area.
11. Test and check the system to bring it back on line. Before bringing the system back on line, test it first so another blackout doesn't occur.
12. Bring the system online to standard configuration. After all necessary repairs have been made, and the repairs have been tested, bring the system online to standard configuration.
13. Contact service center to report completion of repair. Notify the Service Center when all necessary repairs have occurred and the system is back in standard configuration.
14. Generate incident report. Generate the appropriate incident report and file/share as necessary.
15. Ensure contractors are paid. Ensure the proper documentation exists so the Contractors who helped fix the problem get paid in a timely manner.
Ohio State University *Project* Disaster Recovery Plan
GAS
In Case of Emergency Dial 911
Primary Call Order | Department / Secondary Call Order | Name | Work Phone | Cell Phone | Email | Action
1 | Service2Facilities |  | 614.292.6158 | 614.292.6158 | n/a | Notify Department
2 | Send Mass Notification Email
3 | Student Life Security | XXXXX | XXXX | XXXX | XXXX | Notify Department
4 | FOD Assessment Team
| 1 | Jeff Mullins | 614.292.5409 | 740.418.3972 | mullins.279@osu.edu | Notify Department / FOD Assesment Team Members
2
3
4
5 | FOD PM/CM Team
| 1 | OSU PM- |  |  |  | Notify FOD PM/CM Team Members
| 2 | OSU CM-
| 3 | OSU DoP
| 4 | FDC Desk
5
6 | Regulator/Valve/Line Failure Team
| 1 | Jeff Mullins | n/a | 740.418.3972 | mullins.279@osu.edu | Notify Department / Blackout Team Members
| 2 | Ryan Wester
3
7 | Emergency Mgmt & Fire Prev.
|  | Robert Armstrong | 614.247.4276 | 614.247.4276 | armstrong.349@osu.edu | Notify Department
8 | OSU Police
Notify Department
9 | Contractor Staff
Infrastructure & Roadways
| 1 |  |  |  |  | Notify Contractor Staff / Safety Representatives
2
3
4
Cancer & Critical Care Tower
1
2
3
See Reference Sheet in Tab 7
10
| 1 |  |  |  |  | Notify Department
2
3
11
|  | William Crossin | 614.293.4847 | 614.778.3044 | william.crossin@osumc.edu | Notify Department
12 | Dept of Public Safety
Notify Department
13 | TTM
|  | Marshall King | 614.292.9341 | 614.563.0684 | king.414@osu.edu | Notify Department
14 | Environmental Health & Safety
|  | Thomas Novotny | 614.688.1764 |  | novotny.66@osu.edu | Notify Department
15 | Student Life Emergency Mgt.
|  | Jim Thomas |  |  | thomas.1714@osu.edu | Notify Department
Gas FOD Assessment Team Task Assigments
1. Identifies the severity of the situation. Physically inspect the failure.
2. Contact the appropriate individuals (contractors/vendors/employees, etc.) for resolution. Depending on the size and cause of the outage, contact the appropriate team for resolution of the outage.
3. Contact Service Center to start communications. Notify the Service Center of the situation so communications can begin. If possible, include estimated outage time for OSU buildings.
Gas-Regulator, Valve, or Line Failure Team Task Assignments
1. Evacuate the Area. Area of evacuation is contingent on whether the failure is located in/out of a tunnel, wind direction, in/out of a building and amount of leak. If inside a tunnel, take into consideration where the leak will go.
2. Assess Damage. Assess the damage and determine exact location of leak. Also determine who is responsible for repairing the leak.
3. Notify Columbia Gas. If repairing the leak is determined to be the responsibility of Columbia Gas, they should be notified and provided with as much information as possible.
4. Proceed with isolation. Isolate the leak.
5. Contact roads and grounds to dig holes, if necessary. Ensure regulatory requirements for safety, etc. (i.e. OSHA Trenching Regulations) are followed.
6. Determine steps & materials necessary for repair. At this point, determination should be made as to the materials necessary for repair and the steps that need to be taken to ensure a proper and safe repair.
7. Gather materials & labor to perform repairs. OSU staff will make minor repairs, but major ones will be contracted with outside vendor(s).
8. Call contractors. If contractors are necessary to make the repair, the should be called at this time.
9. Contact Service 2 Facilities (aka Service Center) with intermediate report. Keep them updated on the situation.
10. Contact priority buildings. Priority areas should be notified and kept up to date during the incident .
a. Patient care areas (Medical Center, Postle, Optometry)
b. Research animals and livestock (Veterinary Hospital, Vivariums, etc.)
c. Research (Research Foundation, College of Medicine, etc.)
d. Student Affairs (Dormitories, Blackwell Inn, etc.)
e. Other important areas
11. Determine priority building needs. Based on information gathered while notifying priority building, determine the needs of those areas.
12. Repair failure point.
13. Test system. After the repair has been made, test the system.
14. Restore the partial operations. Restore the system to partial operations and confirm stability.
15. Complete restoration. Return the system to normal operations.
16. Contact Service 2 Facilities to report completion. Inform them the problem is fixed and the incident is over.
17. Generate an incident report. A report documenting the incident should be completed and kept on file for future incidents or training, etc.
18. Pay contractors. Ensure purchasing has the proper information and documentation to pay the contractors involved in repairs.
19. Install permanent fix, if necessary. If a temporary repair was used, ensure the repair is fixed with permanent parts.
Ohio State University *Project* Disaster Recovery Plan
WATER
In Case of Emergency Dial 911
Primary Call Order | Department / Secondary Call Order | Name | Work Phone | Cell Phone | Email | Action
1 | Service2Facilities |  | 614.292.6158 | 614.292.6158 | n/a | Notify Department
2 | Send Mass Notification Email
3 | Student Life Security |  |  |  |  | Notify Department
4 | FOD Assessment Team
| 1 | Jeff Mullins | 614.292.6383 | 740.418.3972 |  | Notify Department / FOD Assesment Team Members
2
3
4
5
6
7
8
9
10
11
12
13
14
15
5 | FOD PM/CM Team
| 1 | FOD PM
| 2 | FOD CM
| 3 | FOD DoP |  |  |  | Notify FOD PM/CM Team Members
| 4 | FDC Desk
5
6 | Emergency Mgmt & Fire Prev.
|  | Robert Armstrong | 614.247.4276 | 614.247.4276 | armstrong.349@osu.edu | Notify Department
7 | OSU Police
Notify Department
8 | Contractor Staff
Infrastructure & Roadways
| 1 |  |  |  |  | Notify Contractor Staff / Safety Representatives
2
3
4
1
2
3
See Reference Sheet in Tab 7
9 | PMO
| 1 | Nicole Six | 614.293.5173 | 614.579.3749 | nicole.six@osumc.edu | Notify Department
| 2 | David Fuchs | 614.293.9329 | 614.439.7750 | david.fuchs@osumc.edu
| 3 | Michael Johnson |  | 614.366.8618 | michael.johnson@osumc.edu
10 | Medical Center Staff
|  | William Crossin | 614.293.4847 | 614.778.3044 | william.crossin@osumc.edu | Notify Department
11 | Dept of Public Safety
Notify Department
12 | Transportation and Parking
|  | Marshall King | 614.292.9341 | 614.563.0684 | king.414@osu.edu | Notify Department
13 | Environmental Health & Safety
|  | Thomas Novotny | 614.688.1764 |  | novotny.66@osu.edu | Notify Department
14 | OSUMC Safety
|  | Jim Thomas |  |  | thomas.1714@osu.edu | Notify Department
Water Materials List Stored at XXXXX (Example)
Piping Size and Connection Type
1 ea. – 6”, 8”, 10”, and 12” 150# Mechanical Joint Gate Valve (with curb box/32” stem)
2 ea. – 6”, 8”, 10” and 12” Stainless Steel pipe clamps
20 ft. ea. – 6”, 8”, 10” and 12” Ductile iron, sch. 40 pipe
2 ea. – 6” Mechanical Joint Couplings
2 ea. – 8” Mechanical Joint Couplings
2 ea. – 10” Mechanical Joint Couplings
2 ea. – 12” Mechanical Joint Couplings
Task Assignments
1. Assess damage. The cause and amount of damage should be checked.
2.Isolate point of failure. The point of failure should be isolated by implementing barriers before and after the failure point.
3. Pump water out of damaged site if necessary. Use water pumps to pump water out of the damaged site if necessary.
4. Contact roads & grounds to dig holes, if necessary.
5. Determine steps/tasks & materials necessary for repair. A list of steps/tasks necessary for repair should be completed and shared with all team members. Each step/task should be assigned to the appropriate team member. It may be necessary to make a temporary repair while waiting for permanent repair materials.
6. Gather materials and assemble labor team to perform repairs. Major repairs may have to be contracted with outside vendors.
7. Contact contractors, if necessary. If the damage is too large for OSU FOD employees to handle in a timely manner, contact the appropriate contractor(s) for a timely repair.
8. Contact Service-2-Facilities with an intermediate report. Service-2-Facilities is the communication liaison with customers and other OSU community entities. It is important that Service-2-Facilities be kept up to date with as much information about the outage as possible. This may include how long the outage is expected to continue, locations affected, who is repairing, etc.
9. Contact priority buildings/departments
a. Patient care areas (Medical Center, Postle, Optometry)
b. Research animals and livestock (Veterinary Hospital, Vivariums, etc.)
c. Research (Research Foundation, College of Medicine, etc.)
d. Student Affairs (Dormitories, Blackwell Inn, etc.)
e. Academic Affairs
f. Athletics
g. Administration (Bricker Hall)
e. Other important areas
10. Determine priority buildings/department needs. Depending on when, where and how large the outage is, the aforementioned priority buildings/departments may need additional resources. Provide any appropriate and/or available resources.
11. Repair failure point. Repair the failure point using the available resources (OSU & Outside Vendors)
12. Test system. After the repair, test system.
13. Restore to partial operations and confirm stability. Turn the system on and observe to confirm the repair is adequate.
14. Determine if the water is contaminated (unsafe to consume). If, due to the nature of the outage and/or the repair, the water has become contaminated and is unsafe to consume, take the necessary steps to treat the water to make it safe.
15. If water is contaminated, selectively isolate the contamination. If it is determined that the water is contaminated, isolate the contamination if possible.
16. Complete restoration. After the repair and after the lines are no longer contaminated, complete the restoration to normal operations.
17. Notify Service-2-Facilities of completion. When the system is back in normal operations, it is important to notify Service-2- Facilities.
18. Generate appropriate incident report. An incident report should be generated to documented everything about the incident. The entire team should have input into the report. Someone from the team should be designated as the report writer.
19. Ensure contractors are paid. If contractors were used for the repair, ensure the proper paperwork and communications occur so they paid in a timely manner.
20. Install permanent fix. If due to the unavailability of parts and/or series, a temporary fix was used, install the permanent fix when available.
Ohio State University Disaster Recovery Plan
In Case of Emergency Dial 911
Primary Call Order | Department / Secondary Call Order | Name | Work Phone | Cell Phone | Email | Action
1 | Service2Facilities |  | 614.292.6158 | 614.292.6158 | n/a | Notify Department
2 | Send Mass Notification Email
3 | Hospital Security |  | 614.293.8500 | 614.293.8500 | Security_Managers@osumc.edu | Notify Department
4 | ENGIE Assessment Team
| 1 |  |  |  |  | Notify Department / FOD Assesment Team Members
2
3
5 | FOD PM/CM Team
| 1 | FOD PM- |  |  |  | Notify FOD PM/CM Team Members
| 2 | FOD CM-
| 3 | FOD DoP-
| 4 | FDC Desk
5
6 | Emergency Mgmt & Fire Prev.
|  | Robert Armstrong | 614.247.4276 | 614.247.4276 | armstrong.349@osu.edu | Notify Department
7 | OSU Police
Notify Department
8 | Contractor Staff
Infrastructure & Roadways
Notify Contractor Staff / Safety Representatives
See Reference Sheet in Tab 7
9
| 1 |  |  |  |  | Notify Department
2
3
10
11 | Dept of Public Safety
Notify Department
12 | Transportation and Parking
|  | Marshall King | 614.292.9341 | 614.563.0684 | king.414@osu.edu | Notify Department
13 | Environmental Health & Safety
|  | Thomas Novotny | 614.688.1764 |  | novotny.66@osu.edu | Notify Department
14 | OSUMC Safety
|  | Jim Thomas |  |  | thomas.1714@osu.edu | Notify Department
Steam Material List Stored at xxxx (Example)
1. Schedule 40 steam piping in two (2) 10 foot lengths of each size of piping affected by the work
2. Two (2) 90 degree elbows of each pipe size affected by the work
3. Four (4) sets of flanges and gaskets of each pipe size affected by the work
4. One (1) shut off valve of each pipe size affected by the work and insulation to cover any affected piping repairs
Note: (3) different pipe sizes being affected by this project so all (3) sizes of the items listed above should be on hand in case of emergency repair
All components on hand shall fully meet OSU design standards
Task Assignments
1. Identifies the severity of the situation. Physically inspect the failure or problem.
2. Contact the appropriate team and/or individuals (contractors/vendors/employees, etc.) for resolution. Depending on the size and cause of the situation, contact the appropriate team or individual for resolution.
3. Contact service center to start communications. Notify the Service Center of the situation so communications can begin. If possible, include estimated outage time for OSU buildings.
Ohio State University *Project* Disaster Recovery Plan
Communications
Communicatons Impact Matrix
In Case of Emergency Dial 911
Primary Call Order | Department / Secondary Call Order | Name | Work Phone | Cell Phone | Email | Action
1 | Service2Facilities |  | 614.292.6158 | 614.292.6158 | n/a | Notify Department
2 | Send Mass Notification Email
3 | Hospital Security |  | 614.293.8500 | 614.293.8500 | Security_Managers@osumc.edu | Notify Department
4 | OIT/IT Responders
| 1 | Derek Mayes |  |  |  | Notify Department / FOD Assesment Team Members
| 2 | Brent Reeb
3
4
| 5 | Robert Todd | 614.293.9310 | 614.623.0342 | robb.todd@osumc.edu
| 6 | Shawn Brown | 614.293.9225 | 614.307.5605 | shawn.brown@osumc.edu
| 7 | Joe Weingates | 614.293.0900 | 937.537.9715 | joe.weingates@osumc.edu
| 8 | Dustin Thompson | 614.293.0742 | 614.206.1117 | dustin.thompson@osumc.edu
5 | FOD PM/CM Team
| 1 | OSU PM- |  |  |  | Notify FOD PM/CM Team Members
| 2 | OSU CM-
| 3 | OSU DoP
| 4 | FDC Desk
5
6 | Emergency Mgmt & Fire Prev.
|  | Robert Armstrong | 614.247.4276 | 614.247.4276 | armstrong.349@osu.edu | Notify Department
7 | OSU Police
Notify Department
8 | Messer Staff
Infrastructure & Roadways
| 1 |  |  |  |  | Notify Messer Staff / Safety Representatives
2
3
4
1
2
3
See Reference Sheet in Tab 7
9
| 1 |  |  |  |  | Notify Department
2
3
10
11 | Dept of Public Safety
Notify Department
12 | Transportation and Parking
|  | Marshall King | 614.292.9341 | 614.563.0684 | king.414@osu.edu | Notify Department
13 | Environmental Health & Safety
|  | Thomas Novotny | 614.688.1764 |  | novotny.66@osu.edu | Notify Department
14 | OSUMC Safety
|  | Jim Thomas |  |  | thomas.1714@osu.edu | Notify Department
Communications Materials List Stored at XXXXX
Ohio State University *Project* Disaster Recovery Plan
Hazardous Materials
In Case of Emergency Dial 911
Primary Call Order | Department / Secondary Call Order | Name | Work Phone | Cell Phone | Email | Action
1 | Service2Facilities |  | 614.292.6158 | 614.292.6158 | n/a | Notify Department
2 | Send Mass Notification Email
3 | Hospital Security |  | 614.293.8500 | 614.293.8500 | Security_Managers@osumc.edu | Notify Department
4 | FOD Assessment Team
| 1 | EHS On Call staff | 614.292.1284 | option 1 |  | Notify Department
| 2 | Jeff Henderson | 614.292.1284 | 4.1502 | henderson.202@osu.edu
5 | FOD PM/CM Team
| 1 | FOD PM- |  |  |  | Notify FOD PM/CM Team Members
| 2 | FOD CM-
| 3 | FOD DoP-
| 4 | FDC Desk
5
6 | Emergency Mgmt & Fire Prev.
|  | Robert Armstrong | 614.247.4276 | 614.247.4276 | armstrong.349@osu.edu | Notify Department
7 | OSU Police
Notify Department
8 | Contractor/CM/DB staff
Notify Turner Bovis Staff / Safety Representatives
See Reference Sheet in Tab 7
9 | PMO
| 1 |  |  |  |  | Notify Department
2
3
10 | Medical Center Staff
|  | William Crossin | 614.293.4847 | 614.778.3044 | william.crossin@osumc.edu | Notify Department
11 | Dept of Public Safety
Notify Department
12 | TTM
|  | Marshall King | 614.292.9341 | 614.563.0684 | king.414@osu.edu | Notify Department
13 | Environmental Health & Safety
|  | Thomas Novotny | 614.688.1764 |  | novotny.66@osu.edu | Notify Department
14 | OSUMC Safety
|  | Jim Thomas |  |  | thomas.1714@osu.edu | Notify Department

## EXAMPLE Disaster Recovery Plan
*EXAMPLE Disaster Preparedness Plan*
Ohio State University - *Project* - Disaster Preparedness Plan |  |  |  | Page 1
Plan Date: | 11/8/20XX |  | Revised to incorporate changes as identified in the --/--/, 20-- Disaster Drill and subsequent review metings.
Purpose & Scope of the Plan: | This plan is designed to be used in the event of an incident or disaster affecting the Med Center in whole or in part resulting from actions related to the demolition and construction of the NRDT Project.
Objectives of The Plan: | The Plan is to be set up with time frames for response and action: The responses are specific to the type of incident and are defined within the organization of the incident type.
Organization of the Plan: | The Plan document is intended to be an electronic document written in Microsoft Excel and organized by tabs located at the bottom of the page that represent the type of incident or impact: Each Incident type is a link to the specific actions to be taken relative to the incident type. The intent is for this to be a live document and for users to place this document on their computer desktop and utilize the file in the event of a disaster.
*Project* - Emergency Operations Plan
OSU EHS - HAZMAT SOP
Mass Notification Email Lists
Utility Outage: | Life Gas: |  | Structural: | Fire:
Electrical | Oxygen |  | Collapse
Gas | Steam |  | Excavation cave in
Water
Heat/Steam
Chilled Water
Communications
Utility Maps
Hazardous Materials
Weather: | Crane: |  | Equipment Failure: | Personnel accident:
Code Gray 1 | Collapse |  | Scaffold | Fall
Code Gray 2 | Power failure |  | Equipment/Lift | Cardiac
Distribution: | Jim Hess | jhess@messer.com | Messer
| Ken Miller | kmiller@messer.com | Messer
| Ruth Miller |  | OSU-FDC
| Al Stazzone |  | OSU-FDC
| Molly Ranz-Calhoun |  | OSU-SL
| Jerry Sutton |  | Schooley Caldwell Assoc.
| Tom Matheny |  | Schooley Caldwell Assoc.
| Bob Baumann |  | SMBH
| Stephen Metx |  | SMBH
| Ross Parkman | parkman.3@osu.edu | OSU Utilities
| Mark Jackson | jackson.1529@osu.edu
| Sarah Blouch | blouch.2@osu.edu
| Chris Highfield |  | WA Architects
| Wade Price |  | WA Architects
| Ron Chapman |  | Heapy Engineering
| Gary Eodice |  | Heapy Engineering
| Chuck Paros |  | HKS Inc.
| Bill Brown |  | HKS Inc.
| Eric Walsh |  | Korda
| Brooks Vogel |  | Korda
| Tim Sharp |  | KZF Design
| Bill Wilson |  | KZF Design
| Mitch Acock |  | Acock Associates Architects
Service2Facilities